## RFI Log
RFI Log
Days Open is calculated: days answered minus submitted, or today minus submitted while open.
Sample template with placeholder data. Blue text = cells to edit. Row 5 is an example row: overwrite or delete it.
RFI # | Date Submitted | Subject | Spec / Drawing Ref | Submitted By | Directed To | Response Due | Date Answered | Status | Days Open
RFI-001 | 2026-02-02 | SAMPLE: Clarify door hardware | 08 71 00 / A-501 | GC | Architect | 2026-02-09 |  | Open | 244
Formulas:
Days Open = IF([Date Submitted]="","",IF([Date Answered]<>"",[Date Answered]-[Date Submitted],TODAY()-[Date Submitted]))

## Submittal Matrix
Submittal Matrix
Track each submittal from requirement through review and return.
Sample template with placeholder data. Blue text = cells to edit. Row 5 is an example row: overwrite or delete it.
Submittal # | Spec Section | Description | Subcontractor | Date Required | Date Submitted | Reviewer | Date Returned | Action | Status
SUB-001 | 08 71 00 | SAMPLE: Door hardware schedule | ABC Hardware | 2026-02-10 | 2026-02-06 | Architect |  |  | In Review